## Patients Tracking, Study II
Patient ID | Name | Phone | Replacement Day | Application | Site | ECG Patch SN | SpO2 SN | ECG Patch SN | ECG Patch SN | ECG Patch SN | SpO2 SN | Trial start | 1st Visit | Trial end | Comments | First replace | Second replace | Third replace | Trial start - Patch LOT | 1st Visit - Patch LOT
Icilov
DK03001 | דוד כברי | 050-8383968 050-8491189(בת זוג) | Wednesday |  | Ichilov | 202337/E112265 - VV350 | 2010210923 | 202337/E112305 - VV350 |  |  |  | 15.11.2023 | 11.02.2024 | 16.05.2024 | Replace sensor on Feb 25,2024. Replace sensor on Apr 24,2024 (DS03001). | 25.02.2024 | 24.04.2024
DS03001 | דוד כברי
AY03002 | אלכסנדר יחביץ' | 054-4585812 | Tuesday | every day | Ichilov | 202337/E112323 - VV350 | 2312500283 - Oxyfit | 202337/E112358 - VV350 | 202405/E117849-VV350 |  |  | 06.02.2024 | 06.05.2024 | 13.08.2024 | Replace cellular on Feb 15, 2024, Replace sensor on May 6,2024, Recevied Oxyfit on May 6,2024, sensor replaced on 25.7.2024 | 06.05.2024 | 25.07.2024
MC03003 | כהן מרגלית | 054-2999118 | Tuesday, another day | every 2 days | Ichilov | 202337/E112413 - VV350 | 2312500135 |  |  |  |  | 13.02.2024 | 06.05.2024 | 13.08.2024
FC03004 | כהן פרידה | 052-5304130 | Tuesday | every day | Ichilov | 202337/E112344-VV350 | 2312500081- Oxyfit | 202405/E117797-VV350 |  |  |  | 01.05.2024 | 05.08.2024 | 05.11.2024 | Replace sensor on June 3,2024 (the old data in the old sensor - E117797 was uploaded through Nadav's phone to the same user name - FC03004 on June 4,2024) | 03.06.2024
CH03005 | קרול הופמן | 054-5303308 | Tuesday | every day | Ichilov | 202405/E118029-VV350 | 2312500063- Oxyfit |  |  |  |  | 07.05.2024 | 05.08.2024 | 06.11.2024
MV03006 | מירטה וולך | 050-7332478 | Tuesday |  | Ichilov | 202337/E112423-VV350 | 2201500944 - Oxyfit |  |  |  |  | 09.07.2024 | 09.10.2024 | 14.01.2025 | could not use patch because of chemotherapy for last month of trial. did not do 6MWT for same reason at trial end. Lost oxyfit device.
SK03007 | קלאס סופי | 050-9266999 | Monday |  | Ichilov | 202405/E117832-VV350 | 2312500003 - Oxifit | 202405/E118026-VV350 |  |  |  | 15.07.2024 | 15.10.2024 | 16.12.2024 | Sensor replaced on August 20, 2024 | 20.08.2024
SD03008 | שהרם דרדשתי | 544232376 | Tuesday |  | Ichilov | 202405/E117786-VV350 | 2312500101 - Oxifit | 202337/E112349-VV350 |  |  |  | 16.07.2024 | 07.11.2024 | 05.02.2025 | initial intake was done on 16.7 but the application didn't work. actual start date is 07.08. part of the data from the visit on 07.08 is under RD002 (the username on the tablet the patient recieved- possibly including 6MW data) . Changed sensor due to worn electrodes on 2.1.2025 | 02.01.2025
DB03009 | דרוד בן מנשה | 548305313 | Tuesday | אברבם יאיר שטרן 4 , קרית עקרון | Ichilov | 202405/E117991 | 2312500079- Oxifit |  |  |  |  | 16.07.2024 | לא מתאים למחקר | out
EA03010 | עדנה אבוחסירה | 050-2556039 |  |  | Ichilov | [6 empty] | 17.07.2024 | לא מתאימה למחקר | out
VG03011 | ולדימיר גרדלז'ב | 0546228707 - סבטלנה אשתו | Wednesday |  | Ichilov | 202405/E117971 -VV350 | 2312500004 - oxifit | 202337/E112323-VV350 |  |  |  | 17.07.2024 | 14.10.2024 | 14.01.2025 | Sensor replaced on November 4, 2024 | 04.11.2024
RS03012 | רבקה רחל סלטי | 054-8312606 | Wednesday |  | Ichilov | 202405/E118028 - VV350 | 2312500136 - Oxifit |  |  |  |  | 04.09.2024 | 28.11.2024 | 05.03.2025
VM03013 | ולנטינה משבסקי | 054-6553957 | Monday | אבן גבירול 112, ת"א | Ichilov | 202405/E117858 - VV350 | 2312500311 - Oxyfit | 202405/E117991 - VV350 | 202405/E117971 - VV350 | 202405/E117758 - VV350 |  | 17.09.2024 | 17.12.2024 | 17.03.2024 | Sensor replaced on December 10,2024 - worn electrodes, Another replacement January 13,2025 due to worn electrodes. Another replacement on 23.01.2025, probably the ecg signal between 13-23.01.2025 is with lots of noise. | 10.12.2024 | 13.01.2025 | 23.01.2025
BZ03014 | בוריס זילברמן | 050-7194752 | Monday |  | Ichilov | 202405/E117973-VV350 | 2312500060 -Oxyfit |  |  |  |  | 23.09.2024 | 23.12.2024 | 24.03.2024
EG03015 | גולדמן אדוארד | 052-2508759 | Monday |  | Ichilov | 202405/E117984-VV350 | 2312500167 - Oxyfit |  |  |  |  | 23.09.2024 | יצא מהמחקר עקב חוסר שיתוף פעולה | out
LS03017 | לאה שפירא | 522446366 | Wednesday |  | Ichilov | 202405/E118019 -VV350 | 2312500010-Oxyfit |  |  |  |  | 06.11.2024 | 03.02.2025 | 05.05.2025
IK03016 | אילנה קציר | 054-7659539 | Wednesday |  | Ichilov | 202405/E117849 - VV350 | 2312500133- Oxyfit |  |  |  |  | 13.11.2024 | 11.02.2025
ES03018 | אדי סייק | 050-5863773 | Wednesday |  | Ichilov | [6 empty] | 13.11.2024 | שינה את דעתו | out
IM03019 | אילנה משיח | 054-3972602 | Tuesday |  | Ichilov | 202419/E1R0580 - VV350 | 2312500017 - Oxyfit |  |  |  |  | 07.01.2025 | out |  | Stop the trial, due to rash and allergy.
MA03020 | מרדכי עטרי | 050-8514786 | Wednesday |  | Ichilov | 202419/E1R0579 - VV350 | 2312500079 - Oxyfit |  |  |  |  | 15.01.2025 | 27.04.2025 | out | Stop the trial after three months, when he came to the middle visit, due to rash and allergy.
YS03021 | יואל שגב | 054-9488480 | Monday |  | Ichilov | 202337/E112177 - VV350 | 2312500283 - Oxyfit | 202405/E117748 - VV350 |  |  |  | 20.01.2025 | 21.04.2025 |  |  | 21.04.2025
EM03022 | עזרא מזרחי | 050-3588820 | Tuesday |  | Ichilov | 202337/E112280 - VV350 | 2312500038 - Oxyfit |  |  |  |  | 21.01.2025 | 23.04.2025 | out | Stop the trial, due to rash and allergy.
RL03023 | לריאן רחמים | 054-7781550 - רמי, 0542937790- הרצל (בן של) | Wednesday |  | Ichilov | 202405/E118037 - VV350 | 2312500114 - Oxyfit | 202405/E117832 - VV350 | 202405/E118019 -VV350 |  |  | 22.01.2025 | 23.04.2025 |  | Replaced sensor on February 5, 2025. Replaced another sensor on May 6, 2025. | 05.02.2025 | 06.05.2025
ZV03024 | זהבה וייסברג | 050-8549330, או מספר בית: 03-5713828 | Tuesday | Using our tablet | Ichilov | 202405/E118029 - VV350 | 2312500049 - Oxyfit | 202419/E110397 - VV350 |  |  |  | 28.01.2025 | 29.04.2025 |  | Replaced sensor on March 25, 2025. There is a recording from the first sensor of, 30 seconds on the date: 2025-04-22 - seems like a mistake as she used the new sensor already. | 25.03.2025
sb03025 | שושנה בנישו | 052-6436000 | Sunday |  | Ichilov | 202405/E117854 - VV350 | 2312500231 - Oxyfit |  |  |  |  | 02.02.2025 | 04.05.2025 | out | Patient ID was changed from MB03025 after a few hours. Stop the trial, due to rash and allergy on the middle visit.
RK03026 | רחל קניאס | 054-4696625, או מספר בית: 03-6482963 | Tuesday |  | Ichilov | 202337/E112423 - VV350 | 2312500004 - Oxyfit |  |  |  |  | 04.02.2025 | 06.05.2025
MB03027 | מרדכי בן יצחק | 054-7312118 | Tuesday |  | Ichilov | 202405/E117959 - VV350 | 2312500085 - Oxyfit | 202405/E117953 - VV350 |  |  |  | 11.02.2025 |  |  |  | 09.05.2025 |  |  |  | DS20241123
CY03028 | כהן יחזקאל | 054-6333017 |  |  | Ichilov | 202405/E117953 - VV350 | 2312500081 - Oxyfit |  |  |  |  | 04.03.2025 | out
Soroka
ID04001 | יצחק דראי | 058-5070517 |  |  | Soroka | 202310/C881724 - VV330 | 2010210906 | 202337/E112316 - VV350 | 202337/E112311 - VV350 | 202337/E112301 - VV350 |  | 13.11.2023 | 10.01.2024 | 08.04.2024 | Change Sensor to VV350 on 10-Jan-2024 Change Sensor due to changing phone. Cradle of sensor 316 left in the patient house. Change sensor due to charging problems. | 10.01.2024
AD04002 | אברהם דהאן | 050-3233739 (פרח - בת) | Monday |  | Soroka | 202337/E112051 - VV350 | N.A. |  |  |  |  | 20.11.2023 | הוצא מהמחקר | out | Change Sensor to VV350 and remove SpO2 on 25-Dec-2023 לתאם איסוף הקיט והוצאה מהמחקר | 25.12.2023
AA04003 | עלי | 050-7952134 054-6635080 (אברהים - בן) | Wednesday |  | Soroka | 202337/E112288 - VV350 | 2010210976 |  |  |  |  | 03.01.2024 | הוצא מהמחקר | out
EA04004 | אסתר עמרני | 050-5500193 | Wednesday |  | Soroka | 202337/E112253 - VV350 | 2010211051 |  |  |  |  | 10.01.2024 | 01.04.2024 | 29.05.2024
DP04005 | דליה פרץ ביטון | 054-6276664 דליה | Monday |  | Soroka | 202337/E112341 - VV350 | 2304210904 - Checkme |  |  |  |  | 29.01.2024 | 20.03.2024 | 19.05.2024
AF04006 | ענת פייסט | 054-7776050, הגר (בת) ‐ 054-7776312 | Tuesday |  | Soroka | 202405/E117976 - VV350 | 2312500255 |  |  |  |  | 16.04.2024 |  | 08.08.2024
MA04007 | מאיר אבקסיס | 050-8259798 | Sunday | every day | Soroka | 202337/E112298 - VV350 | 2312500095 - Oxyfit | 202405/E117959 - VV350 | 202405/E118037 - VV350 |  |  | 21.04.2024 | 26.06.2024 | 18.08.2024 | Change Sensor on 23-May-2024, 02-July-2024- | 23.05.2024 | 02.07.2024
SB04008 | סילביה בן אהרון | 052-8464170 |  | משעול סוכות 13/3, ב"ש | Soroka | 202405/E117834 - VV350 | 2312500204 - Oxyfit |  |  |  | 2312500250 - Oxyfit | 27.07.2024 | 15.10.2024 | 08.01.2025 | 2312500204 - Oxyfit- was lost
RS04009 | ראובן רובין סגרון | 052-4881050 | Monday |  | Soroka | 202337/E112301 - VV350 | 2312500231 - Oxyfit |  |  |  |  | 05.08.2024 | 15.10.2024 | 08.01.2025
VS04010 | ורדה סיטבון | 054-3004497 | Wednesday |  | Soroka | 202405/E117855 - VV350 | 2312500012 - Oxyfit |  |  |  |  | 11.09.2024 | 24.12.2024 | 31.03.2025
MN04011 | מתי נקש | 050-7630485 | Monday |  | Soroka | 202405/E117997 - VV350 | 2312500144 - Oxyfit |  |  |  |  | 07.10.2024 | 08.01.2025 | 02.04.2025
MR04012 | משה רחמים |  | Monday |  | Soroka | 202405/E117969 - VV350 | 2312500102 - Oxyfit |  |  |  |  | 06.01.2025 |  |  | Completed 6MWT on 7.1.2025, around 10:29.
HT04013 | חנה טובול | 050-7827159 (קלוד- בעלה) | Tuesday |  | Soroka | 202337/E112323 - VV350 | 2312500239 - Oxyfit |  |  |  |  | 21.01.2025 | 05.05.2025
MC04014 | מרדכי כהן | 052-5024848 | Thursday |  | Soroka | 202419/E1R0564 - VV350 | 2312500072 - Oxyfit |  |  |  |  | 23.01.2025 |  |  | The 6MWT was conducted with the assistance of his wife.
FA04015 | פינה (יוספינה) ארדיטי | 054-6602040 | Monday |  | Soroka | 202337/E112341 - VV350 | 2312500118 - Oxyfit |  |  |  |  | 19.03.2025
Assuta
GM02001 | גולן מדינה | 050-3790003 | Monday |  | Assuta | [6 empty] | 01.04.2024 | הוצא מהמחקר | out
ZB02002 | ציפורה בלומנפלד | 052-8248590 | Monday | every day | Assuta | 202337/E112060- VV350 | 2312500114 - Oxyfit | 202405/E118018 - VV350 |  |  |  | 01.04.2024 | 09.06.2024 | 11.08.2024 | ECG sensor's battery electrode are broken- Change Sensor to VV350 on 02-May-2024 | 02.05.2024
SA02003 | סנדרה אזולאי | 050-8610051 | Sunday |  | Assuta | 202337/E112384 - VV350 | 2312500219 - Oxyfit | 202337/E112319 - VV350 |  |  | 2312500049- Oxifit | 09.06.2024 | 27.08.2024 | 17.11.2024 | ECG sensor's battery electrode are broken- Change Sensor and Oxyfit on 27-Aug-2024 | 27.08.2024
ST02004 | שמעון טובול | 052-2921146 | Wednesday |  | Assuta | 202405/E117839 - VV350 | 2312500085 - Oxyfit |  |  |  |  | 10.07.2024 | 22.09.2024 | 17.11.2024
CB02005 | קמליה בוטז | 054-2638955 | Wednesday |  | Assuta | [6 empty] | 17.07.2024 | 29.09.2024 | 01.12.2024
LP02006 | לימור פנטורין | 052-4755858 |  |  | Assuta | [6 empty] | 19.09.2024 | הוצא מהמחקר | out
AI02007 | אילן אסולין | 054-6120362 | Monday |  | Assuta | 202405/E117853 - VV350 - ERROR | 2312500027 - Oxyfit | 202337/E112301 - VV350 - ERROR | 202405/E117983 - VV350 |  | 2312500131 - Oxyfit | 04.11.2024 |  |  | Change Oxyfit on 13-Mar-2025 | 09.02.2025 | 24.02.2025
IA02008 | איגור אקרמן | 0507196193 חנה (אשתו) | Sunday |  | Assuta | 202419/E1R0493 - VV350 | 2312500063 - Oxyfit |  |  |  |  | 12.01.2025 | 22.04.2025
Barzilai
NL06001 | נדיה לפקוב | 054-6453763 | Monday |  | Barzilai | 202405/E117959 - VV350 | 2312500207 - Oxyfit | 202405/E118014 - VV350 |  |  |  | 18.11.2024 | 17.02.2025 |  | ECG sensor's lost- Change Sensor on 25-Nov-2024 | 25.11.2024
MS06002 | מלכה שמאין | 054-5691818 | Monday |  | Barzilai | [6 empty] | 02.12.2024 | החליטה לעזוב | out
MB06003 | מגי בת ים | 054-7490082 | Sunday |  | Barzilai | 202405/E117761 - VV350 | 2312500273 - Oxyfit |  |  |  |  | 05.01.2025 | 18.03.2025 |  | Completed 6MWT on 14.1.2025
AB06004 | אלכסנדר ביצ'וצקי | 054-4624886- זינה | Sunday |  | Barzilai | 202419/E1R0528 - VV350 | 2312500135 - Oxyfit |  |  |  |  | 09.02.2025 |  |  | 6MWT started ~10:51 on 9 Feb 2025
TB06005 |  |  |  |  | Barzilai | 202419/E110283 - VV350 | 2312500137 - Oxyfit |  |  |  |  | 22.04.2025
LM06006 |  |  |  |  | Barzilai | 202419/E1R0580 - VV350 | 2312500081 - Oxyfit |  |  |  |  | 08.05.2025
Carmel
IR05001 | אילנה רוזנצבייג | 507800278 |  |  | Carmel | 202405/E118037 - VV350 | 2312500101 - Oxyfit |  |  |  |  | 02.03.2025 | החליטה לעזוב | out
AT05002 | אבי טויל | 053-2806010 |  | using our tablet | Carmel | 202419/E110438- VV350 | 2312500095 - Oxyfit |  |  |  |  | 19.03.2025
DD05003 | דוד דוד | 537746685 |  | using our tablet | Carmel | 202405/E118037 - VV350 | 2312500101 - Oxyfit |  |  |  |  | 19.03.2025

## Tablets
Name | Type | Tablets SN | User | Password | PIN Code | Tracking | Sim number | Phone number | Sim company | Data used -12.02
Tab # 1 |  | 352232/11/107491/3 | clinical_1@respirai.com | Respirai2024 | 1111
Tab # 2 |  | 352232/11/107523/3 | clinical_1@respirai.com | Respirai2024 | 222A | office
Tab # 3 |  | 352232/11/107535/7 | clinical_1@respirai.com | Respirai2024 | 3333 | Soroka
Tab # 4 | Tab A | 352232/11/107524/1 | clinical_1@respirai.com | Respirai2024 | 1111 | DD05003 |  |  |  | 4
Tab # 5 | Tab A9 | 351506/55/383637/1 | clinical_1@respirai.com | Respirai2024 | 0000 | ZV03024 | 89972191200054788301 | 559620943 | 019 mobile | 0
Tab #6 | Tab A9 | 351506/55/383644/7 | clinical_1@respirai.com | Respirai2024 | 1111 | shai | 89972191200054788061 | 559620462 | 019 mobile
Tab #7 | Tab A9 | 351506/55/383651/2 | clinical_1@respirai.com | Respirai2024 | 1111 | AT05002 | 89972191200054788079 | 559620470 | 019 mobile
Tab #8 |  |  | clinical_1@respirai.com | Respirai2024 |  | AI02007 |  |  | 019 mobile
Tab #9 |  | 351506/55/532246/1 | clinical_1@respirai.com | Respirai2024 |  | Office
Tab #10 |  | 351506/55/542460/6 | clinical_1@respirai.com | Respirai2024 |  | Office

## ECG Sensors VV350
# | ECG Patch Lot/SN | Model | Frequency | Tracking | Notes | Sending Status
1 | 202337/E112051 | VV350 | 25Hz | Error |  | 13.1.25 - Not sending to Vivalink to keep for emergency - Works fine, no charging box
2 | 202337/E112384 | VV350 | 25Hz | Error | החליפו לסנדרה את המכשיר הזה | 19.1.25 Sent to Vivalink - doesn't charge
3 | 202337/E112253 | VV350 | 25Hz | EA04004 | Can't find the sensor
4 | 202337/E112305 | VV350 | 25Hz | Error |  | Sent to VivaLink
5 | 202337/E112423 | VV350 | 25Hz | RK03026
6 | 202337/E112349 | VV350 | 25Hz | Office
7 | 202337/E112341 | VV350 | 25Hz | FA04015
8 | 202337/E112060 | VV350 | 25Hz | Error (ZB02002) |  | 19.1.25 Sent to Vivalink - doesn't charge
9 | 202337/E112288 | VV350 | 25Hz | Soroka | לאסוף - נמצא ברהט
10 | 202337/E112358 | VV350 | 25Hz | Error |  | Sent to VivaLink
11 | 202337/E112311 | VV350 | 25Hz | ID04001 | Can't find the sensor
12 | 202337/E112316 | VV350 | 25Hz | Error |  | Sent to VivaLink
13 | 202337/E112177 | VV350 | 25Hz | Error |  | Doesn't charge
15 | 202337/E112319 | VV350 | 25Hz | Error |  | 13.1.25 - Not sending to Vivalink to keep for emergency
16 | 202337/E112298 | VV350 | 25Hz | Error |  | 19.1.25 Sent to Vivalink- very worn 3 electrodes
17 | 202337/E112280 | VV350 | 25Hz | Office
18 | 202337/E112413 | VV350 | 25Hz | Error / MC03003 |  | Sent to VivaLink
19 | 202337/E112323 | VV350 | 25Hz | HT04013
20 | 202337/E112301 | VV350 | 25Hz | office
21 | 202405/E117981 | VV350 | 25Hz | never delivered to patient | Can't find the sensor
22 | 202405/E118026 | VV350 | 25Hz | SK03007 Worn electrode |  | 19.1.25 Sent to Vivalink - Noisy signal
23 | 202405/E117983 | VV350 | 25Hz | AI02007
24 | 202405/E117849 | VV350 | 25Hz | IK03016
25 | 202405/E117959 | VV350 | 25Hz | ERROR |  | Doesn't charge
26 | 202405/E117839 | VV350 | 25Hz | Error |  | 13.1.25 - Not sending to Vivalink to keep for emergency
27 | 202405/E117991 | VV350 | 25Hz | VM03013/Error |  | 19.1.25 Sent to Vivalink- very worn 3 electrodes
28 | 202405/E117797 | VV350 | 25Hz | Error |  | 19.1.25 Sent to Vivalink - doesn't charge
29 | 202405/E117748 | VV350 | 25Hz | YS03021
30 | 202405/E117997 | VV350 | 25Hz | Soroka
31 | 202405/E118025 | VV350 | 25Hz | Jonell
32 | 202405/E117973 | VV350 | 25Hz | Office
33 | 202405/E117969 | VV350 | 25Hz | MR04012
34 | 202405/E118019 | VV350 | 25Hz | RL03023
35 | 202405/E117971 | VV350 | 25Hz | Error |  | Thought to be with noise but seems okay after Nadav check. Gave to VM03013 as a replacement on 13.1.25. Took back from VM in 23.1.25 after it seems she has tons of noise
36 | 202405/E117976 | VV350 | 25Hz | AF04006 | Need to pickup from her
37 | 202405/E118029 | VV350 | 25Hz | Office
38 | 202405/E118037 | VV350 | 25Hz | DD05003 |  | RL03023 - had a problem where the app showed lead off all the time. Nadav checked in his phone and it seems okay
39 | 202405/E118018 | VV350 | 25Hz | Error |  | 13.1.25 - Not sending to Vivalink to keep for emergency
40 | 202337/E112384 | VV350 | 25Hz | Error |  | Worn electrodes
41 | 202405/E117858 | VV350 | 25Hz | Error/VM03013 |  | 19.1.25 Sent to Vivalink - doesn't charge
42 | 202405/E117854 | VV350 | 25Hz | Office
43 | 202405/E117758 | VV350 | 25Hz | Ichilov
44 | 202405/E117786 | VV350 | 25Hz | Error/SD03008 |  | 19.1.25 Sent to Vivalink - doesn't charge
45 | 202405/E118028 | VV350 | 25Hz | Error |  | Problematic Charging
46 | 202405/E118014 | VV350 | 25Hz | NL06001
47 | 202405/E117953 | VV350 | 25Hz | MB03027
48 | 202405/E117832 | VV350 | 25Hz | Error |  | Doesn't charge
49 | 202405/E117984 | VV350 | 25Hz | EG03015 | הוא נפטר, הציוד אצלו - ויתרנו על לקחת
50 | 202405/E117855 | VV350 | 25Hz | Soroka
51 | 202405/E117761 | VV350 | 25Hz | MB06003
52 | 202405/E117853 | VV350 | 25Hz | Error |  | Doesn't charge
53 | 202337/E112265 | VV350 | 25Hz | Error |  | Sent to VivaLink
54 | 202419/E1R0528 | VV350 | 25Hz | AB06004
55 | 202419/E1R0580 | VV350 | 25Hz | ML06006
56 | 202419/E1R0564 | VV350 | 25Hz | MC04014
57 | 202419/E1R0579 | VV350 | 25Hz | To be sent to Soroka
58 | 202419/E1R0493 | VV350 | 25Hz | IA02008
59 | 202337/E112344 | VV350 | 25Hz | Error |  | 19.1.25 Sent to Vivalink - doesn't charge
60 | 202419/E110020 | VV350 | 5Hz | MAYO
61 | 202419/E110048 | VV350 | 5Hz | MAYO
62 | 202419/E110420 | VV350 | 5Hz | MAYO
63 | 202419/E110137 | VV350 | 5Hz | MAYO
64 | 202419/E110190 | VV350 | 5Hz | MAYO
65 | 202419/E110397 | VV350 | 5Hz | ZV03024
66 | 202419/E110438 | VV350 | 5Hz | AT05002
67 | 202419/E110434 | VV350 | 5Hz | Office
68 | 202419/E119979 | VV350 | 5Hz | Carmel
69 | 202419/E110242 | VV350 | 5Hz | Office
70 | 202419/E110008 | VV350 | 5Hz | Sent to Soroka
71 | 202419/E110283 | VV350 | 5Hz | TB06005
72 | 202419/E110047 | VV350 | 5Hz | Office
73 | 202419/E110472 | VV350 | 5Hz | Office

## SpO2 Sensors Oxyfit
Oxyfit
| SpO2 SN | Tracking | Notes
1 | 2312500060 | Office
2 | 2312500283 | YS03021
3 | 2312500255 | AF04006
4 | 2312500114 | RL03023
5 | 2312500081 | ML06006
6 | 2312500038 | Office
7 | 2312500239 | HT04013
8 | 2312500004 | RK03026
9 | 2312500171 | Jonell
10 | 2312500167 | EG03015 | הוא נפטר, הציוד אצלו
11 | 2312500204 | SB04008-Lost
12 | 2312500101 | DD05003
13 | 2312500003 | Carmel
14 | 2312500219 | Error | Doesn't turn on
15 | 2312500273 | MB06003
16 | 2312500063 | IA02008
17 | 2312500012 | Soroka
18 | 2312500136 | Office
19 | 2312500079 | Office
20 | 2312500133 | IK03016
21 | 2312500166 | office
22 | 2312500207 | NL06001
23 | 2312500010 | office
24 | 2312500250 | Office
25 | 2312500137 | TB06005
26 | 2312500017 | Office
27 | 2312500102 | MR04012
29 | 2312500095 | AT05002
30 | 2312500085 | MB03027
31 | 2312500311 | Office
32 | 2201500944 | MV03006 -lost
33 | 2312500118 | FA04015
34 | 2312500229 | Office
35 | 2312500072 | MC04014
36 | 2312500049 | ZV03024
37 | 2312500131 | AI02007
38 | 2312500144 | Soroka
39 | 2312500027 | Assuta- ERROR
40 | 23125000231 | Office
41 | 2312500135 | AB06004
42 | 2312500244 | Office
43 | 2312500122 | MAYO
44 | 2312500096 | MAYO
45 | 2312500300 | MAYO
46 | 2312500033 | MAYO
47 | 2312500211 | MAYO

## Equipment Status
Help Columns
ערכות מלאות |  | ערכות שהוחזרו - 15.4 |  | ערכות מלאות - 07.05 | [21 empty] | Trial end | 1st Visit | Trial start | Patient
במשרד - 13.5 | 2 | איכילוב | 1 (רק של אק"ג - ורינה אמרה שהקופסת חיישן אק"ג לא עובדת) | איכילוב |  | 0 | [19 empty] | 2024-05-16 | 2024-02-11 | 2023-11-15 | DK03001
נדב - 4.5 | 0 | אסותא | 0 | אסותא |  | 1 (ללא סנסור ומד סטורציה) ועוד סטורציה תקול | [19 empty] | #NUM! | #NUM! | #NUM! | DS03001
שי - 11.5 | 0 | סורוקה | 3 (אחד החיישני סטורציה הוא הישן) + טאבלט | סורוקה |  | 0 (+סנסור) | [19 empty] | 2024-08-13 | 2024-05-06 | 2024-02-06 | AY03002
רייצ'ל- 18.3 | 0 | ברזילי | 0 | ברזילי |  | 0 | [19 empty] | 2024-08-13 | 2024-05-06 | 2024-02-13 | MC03003
אסף | 0 | כרמל | 0 | כרמל |  | 1 | [19 empty] | 2024-11-05 | 2024-08-05 | 2024-05-01 | FC03004
נועם -11.5 | 1 |  |  | ברזילי |  | 0 | [19 empty] | 2024-11-06 | 2024-08-05 | 2024-05-07 | CH03005
[26 empty] | 2025-01-14 | 2024-10-09 | 2024-07-09 | MV03006
[26 empty] | 2024-12-16 | 2024-10-15 | 2024-07-15 | SK03007
כמויות ציוד מעבר לערכות המלאות | [25 empty] | 2025-02-05 | 2024-11-07 | 2024-07-16 | SD03008
סוג ציוד | במשרד - 13.5 | נדב - 15.4 | שי - 11.5 | נועם | אסף | [20 empty] | #VALUE! | #VALUE! | 2024-07-16 | DB03009
חיישני אק"ג | 4 | 0 | 0 | 0 | 0 | [20 empty] | #VALUE! | #VALUE! | 2024-07-17 | EA03010
חיישני סטורציה | 9 | 0 | 0 | 0 | 0 | [20 empty] | 2025-01-14 | 2024-10-14 | 2024-07-17 | VG03011
מדבקות אק"ג | 12 | 0 | 0 | 0 | 0 | [20 empty] | 2025-03-05 | 2024-11-28 | 2024-09-04 | RS03012
פדי אלכוהול | 120 | 20 | 30 | 0 | 0 | [20 empty] | 2024-03-17 | 2024-12-17 | 2024-09-17 | VM03013
שקעים | 2 | 0 | 0 | 0 | 0 | [20 empty] | 2024-03-24 | 2024-12-23 | 2024-09-23 | BZ03014
ספריי אלכוהול | 1 | 0 | 0 | 0 | 0 | [20 empty] | #VALUE! | #VALUE! | 2024-09-23 | EG03015
ג'ל נגד גירוי | 30 | 0 | 10 | 0 | 0 | [20 empty] | 2025-05-05 | 2025-02-03 | 2024-11-06 | LS03017
סכיני גילוח | 50 | 10 | 0 | 0 | 0 | [20 empty] | #NUM! | 2025-02-11 | 2024-11-13 | IK03016
[26 empty] | #VALUE! | #VALUE! | 2024-11-13 | ES03018
[26 empty] | #NUM! | #VALUE! | 2025-01-07 | IM03019
| אפריל | מאי | [23 empty] | #VALUE! | 2025-04-27 | 2025-01-15 | MA03020
גיוסים מתוכננים להמשך - 31.03 | 2 | 2 | [23 empty] | #NUM! | 2025-04-21 | 2025-01-20 | YS03021
[26 empty] | #VALUE! | 2025-04-23 | 2025-01-21 | EM03022
[26 empty] | #NUM! | 2025-04-23 | 2025-01-22 | RL03023
גיוסי עבר | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | [6 empty] | #NUM! | 2025-04-29 | 2025-01-28 | ZV03024
| 2 | 0 | 2 | 2 | 0 | 3 | 2 | 1 | 7 | 1 | 4 | 1 | 4 | 0 | 10 | 4 | 3 | 0 | 0 | [6 empty] | #VALUE! | 2025-05-04 | 2025-02-02 | sb03025
| 2023-11-01: יש לשים לב שבביקורי אמצע וסיום לא התייחסתי לכך שבאסותא אנחנו מגייסים לארבעה חודשים | [6 empty] | #NUM! | 2025-05-06 | 2025-02-04 | RK03026
ביקורי אמצע | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | #NUM! | #NUM! | 2025-02-11 | MB03027
|  |  |  | 2 | 0 | 2 | 2 | 0 | 3 | 2 | 1 | 7 | 1 | 4 | 1 | 4 | 0 | 10 | 4 | 3 | 0 | 0 |  |  |  | #NUM! | #VALUE! | 2025-03-04 | CY03028
[26 empty] | #NUM! | #NUM! | #NUM! | Soroka
ביקורי סיום | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2024-04-08 | 2024-01-10 | 2023-11-13 | ID04001
[7 empty] | 2 | 0 | 2 | 2 | 0 | 3 | 2 | 1 | 7 | 1 | 4 | 1 | 4 | 0 | 10 | 4 | 3 | 0 | 0 | #VALUE! | #VALUE! | 2023-11-20 | AD04002
[26 empty] | #VALUE! | #VALUE! | 2024-01-03 | AA04003
ממוצע גיוסים חודשיים | 2023-11-01: 3.6667 | 2024-05-29 | 2024-04-01 | 2024-01-10 | EA04004
[26 empty] | 2024-05-19 | 2024-03-20 | 2024-01-29 | DP04005
[26 empty] | 2024-08-08 | #NUM! | 2024-04-16 | AF04006
[26 empty] | 2024-08-18 | 2024-06-26 | 2024-04-21 | MA04007
תקלות בחיישנים | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 |  | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | [9 empty] | 2025-01-08 | 2024-10-15 | 2024-07-27 | SB04008
| 0 | 1 | 1 | 1 |  | 0 | 1 | 3 | 1 | 2 | 2 | 0 | 0 | 2 | 1 | 4 | [9 empty] | 2025-01-08 | 2024-10-15 | 2024-08-05 | RS04009
סך תקלות עד ינואר 2025 | 15 | [24 empty] | 2025-03-31 | 2024-12-24 | 2024-09-11 | VS04010
[26 empty] | 2025-04-02 | 2025-01-08 | 2024-10-07 | MN04011
[26 empty] | #NUM! | #NUM! | 2025-01-06 | MR04012
[26 empty] | #NUM! | 2025-05-05 | 2025-01-21 | HT04013
[26 empty] | #NUM! | #NUM! | 2025-01-23 | MC04014
[26 empty] | #NUM! | #NUM! | 2025-03-19 | FA04015
[26 empty] | #NUM! | #NUM! | #NUM! | Assuta
[26 empty] | #VALUE! | #VALUE! | 2024-04-01 | GM02001
[26 empty] | 2024-08-11 | 2024-06-09 | 2024-04-01 | ZB02002
[26 empty] | 2024-11-17 | 2024-08-27 | 2024-06-09 | SA02003
[26 empty] | 2024-11-17 | 2024-09-22 | 2024-07-10 | ST02004
[26 empty] | 2024-12-01 | 2024-09-29 | 2024-07-17 | CB02005
[26 empty] | #VALUE! | #VALUE! | 2024-09-19 | LP02006
[26 empty] | #NUM! | #NUM! | 2024-11-04 | AI02007
[26 empty] | #NUM! | 2025-04-22 | 2025-01-12 | IA02008
[26 empty] | #NUM! | #NUM! | #NUM! | Barzilai
[26 empty] | #NUM! | #NUM! | #NUM!
[26 empty] | #NUM! | 2025-02-17 | 2024-11-18 | NL06001
[26 empty] | #VALUE! | #VALUE! | 2024-12-02 | MS06002
[26 empty] | #NUM! | 2025-03-18 | 2025-01-05 | MB06003
[26 empty] | #NUM! | #NUM! | 2025-02-09 | AB06004
[26 empty] | #NUM! | #NUM! | #NUM! | Carmel
[26 empty] | #VALUE! | #VALUE! | 2025-03-02 | IR05001
[26 empty] | #NUM! | #NUM! | 2025-03-19 | AT05002
[26 empty] | #NUM! | #NUM! | 2025-03-19 | DD05003

## ECG Sensors VV330
VV330
# | ECG Patch Lot/SN | Model | Frequency | Tracking
1 | 202203/c874100 | VV330 | 5Hz
2 | 201221/c762938 | VV330 | 5Hz
3 | 202121/c762923 | VV330 | 5Hz
4 | 202129/c866936 | VV330 | 5Hz | Vladimir
5 | 202203/c874106 | VV330 | 5Hz
6 | 202203/c875630 | VV330 | 5Hz
7 | 202203/c874110 | VV330 | 5Hz
8 | 202203/c874114 | VV330 | 5Hz | Noam
9 | 202203/c874157 | VV330 | 5Hz
10 | 202203/c874135 | VV330 | 5Hz
11 | 202203/c874150 | VV330 | 5Hz
12 | 202203/c875485 | VV330 | 5Hz
13 | 202203/c874128 | VV330 | 5Hz | Office
14 | 202203/c874156 | VV330 | 5Hz | Office
15 | 202203/c874104 | VV330 | 5Hz
16 | 202129/c866935 | VV330 | 5Hz | Nimrod - USA
17 | 202203/c875484 | VV330 | 5Hz
18 | 202310/c881738 | VV330 | 125Hz
19 | 202310/c882016 | VV330 | 125Hz
20 | 202310/c881748 | VV330 | 25Hz | Vladimir
21 | 202310/c881724 | VV330 | 25Hz | Error | Sent to VivaLink
22 | 202311/c883074 | VV330 | 25Hz
23 | 202311/c882456 | VV330 | 25Hz
24 | 202311/c8827438 | VV330 | 25Hz
25 | 202311/c8827467 | VV330 | 25Hz
26 | 202311/c882475 | VV330 | 25Hz
27 | 202311/c882424 | VV330 | 25Hz
28 | 202311/c882457 | VV330 | 25Hz
29 | 202311/c883108 | VV330 | 25Hz
30 | 202311/c882237 | VV330 | 25Hz
31 | 202311/c882585 | VV330 | 25Hz
32 | 202311/c882582 | VV330 | 25Hz
33 | 202311/c882425 | VV330 | 25Hz
34 | 202311/c882419 | VV330 | 25Hz
35 | 202311/c882422 | VV330 | 25Hz
36 | 202311/c883104 | VV330 | 25Hz
37 | 202311/c882462 | VV330 | 25Hz
38 | 202311/c882236 | VV330 | 25Hz
39 | 202311/c882238 | VV330 | 25Hz
40 | 202311/c882421 | VV330 | 25Hz | Nimrod -USA
41 | 202311/c882472 | VV330 | 25Hz
42 | 202425/C983954 | VV330 | 25Hz

## SpO2 Sensors Checkme
Checkme
| SpO2 SN | Tracking
1 | 2010210998
2 | 2010210987 | Error 4
3 | 2010210976
4 | 2010210931
5 | 2010210906
6 | 2010210807
7 | 2010210923
8 | 2010210937
9 | 2010211051
10 | 2010210937
11 | 2304211046 | Nimrod
12 | 2304210904

## ECG patch adhesive (4 pcs)
Quantity | Expiration date | Updated on
120 (X 4 Units) | 2023-09-06
85(X 4 Units) | 2023-09-06 | 2023-01-06
200(X 1 Units) | 17/04/2024 | 2023-12-06
1500(X 1 Units) | 15/05/2024 | 2023-12-06

## Gift Cards
Gift Card SN | NIS | Patient #
8614 | 500 | DK01
1191 | 500 | MC03
9577 | 500 | AY02
4671 | 500 | ch05
1779 | 500 | NL06001
8010035749179070 | 500 | FC03004
8010033455269839 | 500 | MV03006
8010035156437094 | 500 | VG03011
8010035154159286 | 500 | SK03007
8010033110124759 | 1000 | IK03016
8010033103290260 | 1000 | BZ03014
8010033103999076 | 1000 | RS03012
8010033106833967 | 1000 | VM03013
8010033109460057 | 1000 | SD03008
8010033507617746 | 1000 | SK07
NA | 1000 | DK01
NA | 1000 | MC03
NA | 1000 | AY02
NA | 1000 | FC04
NA | 1000 | CH05
NA | 1000 | MV06
8010042804274978 | 1000 | VG11
8010048835173154 | 300 | Office
8010048834580805 | 300 | Office
8010048835163320 | 300 | Office
8010038520021735 | 50 | Office
8010038419119970 | 50 | Office
8010035847905350 | 500 | SD03008
8010035849153538 | 500 | RS03012
8010037601310348 | 1000 | MB03027
8010038664466159 | 1000 | RL03023
8010031069800668 | 500 | VM03013
8010031069371835 | 500 | LS03017
8010031072539634 | 500 | BZ03014
8010031071384248 | 500 | MB06003
8010049884823483 | 1000 | YS03021
8010049885755916 | 1000 | sb03025
8010049885638203 | 1000 | ZV03024
8010049885050003 | 1000 | MB03027-Ichilov
8010049884950666 | 1000 | MA03020
8010049884849843 | 1000 | RK03026
8010037447127641 | 1000 | EM03022
8010033915128377 | 500 | Office
8010033916063524 | 500 | Office
8010033918014715 | 500 | Office
8010033917014104 | 500 | Office
8010033912750512 | 500 | Office
8010033912985753 | 500 | Office
8010033913851525 | 500 | IK03016-Ichilov
8010033914555935 | 500 | Office
8010033913767754 | 500 | Office
8010033915035366 | 500 | Office
8010031003965254 | 250 | Office
8010031005354457 | 250 | Office
8010031004648446 | 250 | Office